## Sheet1
Work Package | Task | Start Date | End Date | 2023 | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027
|  |  |  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
WP1 | WP1: Review of PGS storage landscape and Solid storage principles | 2023-10-01 | 31/03/2024 | bar: 2023 Q4 to 2024 Q1
| T1.1: Literature Review | 2023-10-01 | 31/03/2024 | bar: 2023 Q4 to 2024 Q1
| T1.2: Paper Composition | 16/12/2023 | 31/03/2024 | bar: 2023 Q4 to 2024 Q1
| T1.3: Peer-review and Integration of Feedback | 2024-01-01 | 30/06/2024 | bar: 2024 Q1 to 2024 Q2
| M1: Manuscript Submission | 2024-06-30 | 30/06/2024 | bar: 2024 Q2
WP2 | WP2: Genomic Data Ingestion to Solid Pod | 2023-10-01 | 31/03/2024 | bar: 2023 Q4 to 2024 Q1
| T2.1: Benchmark VCF files | 2023-10-01 | 31/12/2023 | bar: 2023 Q4 to 2024 Q1
| T2.2: Solid CSS pod building | 2024-01-01 | 31/03/2024 | bar: 2023 Q4 to 2024 Q1
| T2.3: Initial PGS data file upload interface | 2024-04-01 | 30/06/2024 | bar: 2024 Q1 to 2024 Q2
| T2.4: Demo of interface preparation / presentation | 2024-04-01 | 30/06/2024 | bar: 2024 Q1 to 2024 Q2
| M2: Manuscript / Conference Proceedings | 31/03/2024 | 30/06/2024 | bar: 2024 Q2
WP3 | WP3: Genomic Data Formatting Interface Development | 2024-04-01 | 31/12/2026 | bar: 2023 Q4 to 2026 Q4
| T3.1: Choosing a PGS data ontology | 2024-07-01 | 31/12/2024 | bar: 2024 Q3 to 2024 Q4
| T3.2: RDF conversion strategy experimentation | 2024-07-01 | 2024-12-31 | bar: 2024 Q3 to 2024 Q4
| T3.3: Native PGS to RDF data conversion experimentation | 2025-01-01 | 2025-03-31 | bar: 2025 Q1 to 2025 Q2
| T3.4: Native PGS to RDF data conversion optimization | 2025-07-01 | 31/12/2026 | bar: 2025 Q3 to 2026 Q4
| T3.6: Results organization, manuscript composition, and/or presentation prepatation | 2025-07-01 | 2025-12-31 | bar: 2025 Q3 to 2025 Q4
| M3: Manuscript / Conference Proceedings | 2025-12-31 | 2025-12-31 | bar: 2025 Q4
WP4 | WP4: Query Optimization | 2024-07-01 | 31/12/2026 | bar: 2023 Q4 to 2026 Q4
| T4.1: Review of Linked-data Traversal Algorithms | 2024-10-01 | 2024-03-31 | bar: 2024 Q4 to 2025 Q1
| T4.2: Single Solid pod query experimentation (fundamentals) | 2025-01-01 | 30/06/2025 | bar: 2025 Q1 to 2025 Q2
| T4.3: Materialization vs Virtualization experimentation (single pod) | 2025-04-01 | 30/09/2025 | bar: 2025 Q2 to 2025 Q3
| T4.4: Query algorithm speed improvment experimentation (single pod) | 2025-04-01 | 30/09/2025 | bar: 2025 Q2 to 2025 Q3
| T4.5: Multiple Solid pods query experimentation (fundamentals) | 2025-10-01 | 31/03/2026 | bar: 2025 Q4 to 2026 Q1
| T4.6: Materialization vs Virtualization experimentation (multiple pods) | 2026-01-01 | 31/12/2026 | bar: 2026 Q1 to 2026 Q4
| T4.7: Query algorithm speed improvment experimentation (multiple pods) | 2026-01-01 | 31/12/2026 | bar: 2026 Q1 to 2026 Q4
| T4.8: Results organization, manuscript composition, and/or presentation prepatation | 2026-07-01 | 31/12/2026 | bar: 2026 Q3 to 2026 Q4
| M4: Manuscript / Conference Proceedings | 2026-12-31 | 31/12/2026 | bar: 2026 Q4
WP5 | WP5: Integration of FHIR / OMOP-CDH standards and Beacons resource establishment | 2024-04-01 | 31/12/2026 | bar: 2023 Q4 to 2026 Q4
| T5.1: Application of FHIR and OMOP-CDH standards to VCF data storage | 2024-04-01 | 31/03/2025 | bar: 2024 Q2 to 2025 Q1
| T5.2: Application of PENGQUIN project endpoints as Beacon resources | 2026-04-01 | 31/12/2026 | bar: 2026 Q2 to 2026 Q4
| M5: Manuscript / Conference Proceedings | 2026-12-31 | 31/12/2026 | bar: 2026 Q4
Ph.D. Dissertation |  | 2027-04-01 | 30/09/2027 | bar: 2023 Q4 to 2027 Q3